## Migration Checklist
CORTEVA AGRISCIENCE — ANALYTICS PLATFORM SEPARATION MIGRATION CHECKLIST
SAS ¦ Spotfire ¦ Power BI Gateway Dev → Sandbox → Prod Windows Server upgrade to current supported version (2022/2025 TBD)
ROW COLOR: WHITE = You (solo) GREEN = Parallel (can overlap) BLUE = Delegate to Jake/SAS Admin/IT AMBER = Joint / collaborative STATUS: Not Started ¦ In Progress ¦ Complete ¦ Blocked
# | Task | Completion Criteria / Definition of Done | Phase | Owner | Parallel? | Status | Platform(s) | Notes / Dependencies
PHASE 0 · PRE-START
1 | Review all materials from Saritha & Jake interviews | Notes consolidated; open questions logged; nothing assumed | 0 · Pre-Start | You | No | Not Started | All | Include CMDB fragmentation finding from Jake as a Day 1 risk item
2 | Confirm contract signed and access provisioned | Written confirmation received; start date locked; NDAs complete | 0 · Pre-Start | You + Palmer Group | No | Not Started | All | Kristi / Sarah at The Palmer Group
3 | Schedule kick-off with Saritha and Jake | Meeting on calendar; agenda sent in advance | 0 · Pre-Start | You | No | Not Started | All | Do this Day 1
4 | Obtain environment access: Dev, Sandbox, Prod | Can log in to all three tiers on all three platforms; access verified | 0 · Pre-Start | Jake / IT | Yes | Not Started | SAS / Spotfire / PBI | Delegate request to Jake; follow up daily until resolved
5 | Confirm target Windows Server version with Saritha and Jake | Written agreement on OS target version (2022, 2025, or other); documented and signed off | 0 · Pre-Start | You + Saritha + Jake | No | Not Started | Infrastructure | Jake indicated latest supported version may be target — get this confirmed in writing before any planning. Current latest is Server 2025.
PHASE 1 · DISCOVERY
6 | Document current SAS environment (version, host, config, scheduled jobs) | SAS version, grid/Viya config, all scheduled jobs, data sources fully documented | 1 · Discovery | You + SAS Admin | Yes | Not Started | SAS | Jake has been primary SAS admin ~2.5 years since predecessor retired — no formal handoff occurred. Gaps are likely.
7 | Document current Spotfire environment (version, host, data connections, auth) | Spotfire server version, all data connections, user groups, auth method documented | 1 · Discovery | Jake | Yes | Not Started | Spotfire | Jake leads; you validate output against what you expect to see
8 | Document current Power BI Gateway (version, data sources, credentials, auth) | Gateway version, all registered data sources, service accounts / AD groups documented | 1 · Discovery | Jake | Yes | Not Started | Power BI | Auth setup and credential storage are highest risk — press for specifics
9 | Audit and consolidate dependency tracking across all platforms | Full inventory of where dependency/config tracking currently lives; gaps and overlaps identified; single working map produced | 1 · Discovery | You + Jake | No | Not Started | All | IMPORTANT: Jake indicated dependency tracking is fragmented with no single source of truth — 'all over the place.' There is no reliable CMDB baseline to start from. Audit ALL sources (ServiceNow if present, Datadog, spreadsheets, tribal knowledge) and build a unified map before touching anything.
10 | Trace and document all database connections for the separated environment | Full list of DB endpoints confirmed; which persist post-separation vs. which need new instances identified | 1 · Discovery | You + DBA | Yes | Not Started | All | ~140 users (35% of 400) moving to new IT domain. Confirm which DB connections follow them vs. stay with parent.
11 | Inventory all servers in scope for OS upgrade and separation | Hostnames, roles, installed software, current OS patch level documented for every server across all 3 platforms | 1 · Discovery | Jake / IT | Yes | Not Started | Infrastructure | Scope: how many servers total? All 3 platforms on same hosts or separate?
12 | Assess all documentation gaps and flag risks to Saritha | Gap report delivered; risks ranked; Saritha has acknowledged and prioritized | 1 · Discovery | You | No | Not Started | All | Fragmented dependency tracking from #9 will likely dominate this report. Do not proceed to Planning until reviewed.
PHASE 2 · PLANNING
13 | Confirm OS upgrade sequence: upgrade first, then separate (as Jake agreed) | Written agreement that OS upgrade precedes separation work; sequencing documented | 2 · Planning | You + Saritha + Jake | No | Not Started | Infrastructure | Jake agreed: upgrade OS before doing the spinoff separation. Lock this in writing.
14 | Confirm target OS version and obtain IT approval | Target version (2022/2025/other) formally approved by IT; procurement/licensing confirmed | 2 · Planning | Saritha + IT | No | Not Started | Infrastructure | Delegate approval to Saritha; you need the answer before build work begins
15 | Build consolidated dependency map as single source of truth | All platform dependencies, DB connections, service accounts, and AD groups in one verified document; Jake and Saritha sign off | 2 · Planning | You | No | Not Started | All | This replaces the fragmented tracking Jake described. Non-negotiable foundation for safe migration.
16 | Confirm migration sequence across platforms (SAS / Spotfire / PBI order) | Agreed platform migration order documented and signed off by Saritha | 2 · Planning | You + Saritha | No | Not Started | All | Dependencies between platforms may dictate order — validate against the map from #15
17 | Build rollback plan for each platform and each environment tier | Rollback steps documented for Dev, Sandbox, and Prod for all 3 platforms; reviewed by Jake | 2 · Planning | You | Yes | Not Started | All | Script-level diffs captured before any change. No exceptions.
18 | Establish change control process for migration duration | Change log template in place; agreed tool (Jira or equivalent) configured; Jake and Saritha aware | 2 · Planning | You | No | Not Started | All | Propose Jira if available; minimum: shared timestamped log
19 | Establish source control for all scripts and configs being migrated | Git repo (or agreed tool) initialized; baseline snapshots committed before any changes made | 2 · Planning | You | No | Not Started | SAS / Spotfire / PBI | Zero changes without a committed baseline.
20 | Review and validate Saritha's migration playbook draft | Playbook reviewed; gaps annotated; feedback returned to Saritha | 2 · Planning | You + Saritha | Yes | Not Started | All | Playbook was in progress per Saritha — do not wait for final version
21 | Prepare and present 2-week next-steps plan to Saritha and Jake | Presentation delivered within 2 weeks of start; plan accepted or revised with agreement | 2 · Planning | You | No | Not Started | All | Jake specifically requested this deliverable. Include OS upgrade sequencing, separation scope (~140 users / new IT domain), and dependency audit findings.
22 | Define success criteria and sign-off process for each environment | Written definition of done for Dev, Sandbox, and Prod accepted by Saritha | 2 · Planning | You + Saritha | No | Not Started | All | Protects you at contract end
PHASE 3 · OS UPGRADE (Pre-Separation)
23 | Stand up new Windows Server (target version) for each platform in Dev | Servers provisioned, patched, domain-joined, accessible; confirmed by IT | 3 · OS Upgrade | IT / Jake | Yes | Not Started | Infrastructure | Target version TBD — do not begin until #14 is complete
24 | Migrate SAS to upgraded OS in Dev; validate all jobs and configs | SAS running on new OS in Dev; all scheduled jobs execute; output matches baseline | 3 · OS Upgrade | You + SAS Admin | No | Not Started | SAS | Validate against documented baseline from Phase 1 #6
25 | Migrate Spotfire to upgraded OS in Dev; validate connections and auth | Spotfire running on new OS; data connections restored; test users authenticated | 3 · OS Upgrade | Jake | Yes | Not Started | Spotfire | Jake leads; you validate
26 | Migrate Power BI Gateway to upgraded OS in Dev; validate all data sources | Gateway registered on new OS; all data sources active; test refresh succeeds | 3 · OS Upgrade | You + Jake | Yes | Not Started | Power BI | Re-test all service accounts and auth — do not assume config carries cleanly
27 | Promote OS upgrade through Sandbox and Prod with full regression each tier | All platforms running on upgraded OS in Sandbox and Prod; full regression passed; Saritha sign-off obtained | 3 · OS Upgrade | You + Jake + Saritha | No | Not Started | All | Complete OS upgrade across all tiers before beginning separation work
PHASE 4 · DEV SEPARATION BUILD
28 | Stand up new separated Dev environment in new IT domain | New domain infrastructure provisioned; accessible; confirmed by IT | 4 · Dev Separation | IT / Jake | Yes | Not Started | Infrastructure | New company = new IT domain. Confirm AD, DNS, networking scope with IT before start.
29 | Install and configure SAS in separated Dev on new domain | SAS installed; config matches source baseline; test jobs run successfully | 4 · Dev Separation | You + SAS Admin | No | Not Started | SAS | ~140 users (35% of 400) in new domain. Validate user access against new AD.
30 | Install and configure Spotfire in separated Dev on new domain | Spotfire running; data connections restored; user groups migrated to new domain; auth confirmed | 4 · Dev Separation | Jake | Yes | Not Started | Spotfire | Jake leads; you validate against Phase 1 documentation
31 | Install and configure Power BI Gateway in separated Dev on new domain | Gateway registered; all data sources reconnected; new domain credentials validated; test refresh succeeds | 4 · Dev Separation | You + Jake | Yes | Not Started | Power BI | Auth and service accounts must be recreated in new domain — highest risk item
32 | Reconnect and validate all DB dependencies in separated Dev (per unified map #15) | Every connection on the consolidated dependency map verified working in separated Dev | 4 · Dev Separation | You | No | Not Started | All | This is where fragmented legacy tracking will cause problems. Trust only the map from #15.
33 | Full regression in separated Dev: jobs, reports, data refreshes | All known scheduled jobs and reports run successfully; output matches baseline | 4 · Dev Separation | You | No | Not Started | All | Capture baseline from current prod first for comparison
34 | Document all issues found in separated Dev; confirm resolutions | Issue log complete; all critical items resolved before Sandbox | 4 · Dev Separation | You | No | Not Started | All | Nothing moves to Sandbox with open critical issues
PHASE 5 · SANDBOX SEPARATION
35 | Stand up separated Sandbox environment in new IT domain | Sandbox provisioned and accessible; confirmed by IT | 5 · Sandbox | IT / Jake | Yes | Not Started | Infrastructure | Can run in parallel with Dev regression
36 | Promote all platform configs from separated Dev to separated Sandbox | All 3 platforms running in Sandbox; change log updated; diffs captured | 5 · Sandbox | You + Jake | No | Not Started | All | Promote only — no manual changes in Sandbox
37 | Reconnect and validate all DB dependencies in separated Sandbox | Every connection on the consolidated dependency map verified in Sandbox | 5 · Sandbox | You | No | Not Started | All | Run the same checklist as Dev #32 — again
38 | Full UAT in separated Sandbox with ~140 affected users / stakeholders | Key users tested and signed off; no critical issues open | 5 · Sandbox | Saritha / Users | Yes | Not Started | All | Saritha owns sign-off; you support and document results
39 | Sandbox sign-off from Saritha before Prod cutover | Written sign-off from Saritha confirming Sandbox separation complete | 5 · Sandbox | Saritha | No | Not Started | All | Do not schedule Prod cutover without this in writing
PHASE 6 · PROD SEPARATION CUTOVER
40 | Schedule Prod cutover window; communicate to all ~140 affected users | Cutover date/time confirmed; maintenance window communicated; rollback decision point agreed | 6 · Prod Cutover | You + Saritha | No | Not Started | All | Pick low-usage window; have rollback steps open before starting
41 | Take final snapshot / backup of current Prod before cutover | Full backup of all 3 platforms confirmed; integrity verified; stored securely | 6 · Prod Cutover | You + IT | No | Not Started | All | This is your rollback safety net — do not skip or abbreviate
42 | Stand up separated Prod environment in new IT domain | Prod servers provisioned, patched, domain-joined, accessible | 6 · Prod Cutover | IT / Jake | No | Not Started | Infrastructure | Should be provisioned before cutover window opens
43 | Promote all platform configs to separated Prod via change control | All 3 platforms running in separated Prod; change log updated | 6 · Prod Cutover | You + Jake | No | Not Started | All | Follow exact same sequence as Sandbox — no improvising
44 | Reconnect and validate all DB dependencies in separated Prod | Every connection on the consolidated dependency map verified live in Prod | 6 · Prod Cutover | You | No | Not Started | All | Run the checklist a third time. This is Prod.
45 | Go / No-Go decision with Saritha at rollback decision point | Explicit go/no-go documented; rollback executed within agreed window if no-go | 6 · Prod Cutover | You + Saritha | No | Not Started | All | Have rollback steps open and ready before this conversation
PHASE 7 · VALIDATION
46 | Full regression in separated Prod: jobs, reports, data refreshes | All scheduled jobs completed; report outputs match pre-migration baseline | 7 · Validation | You | No | Not Started | All | Compare against baseline captured before cutover
47 | Monitor platform health for 48-72 hours post-cutover | No critical alerts; any anomalies investigated and resolved or accepted | 7 · Validation | You + Jake | No | Not Started | All | Agree on alert routing with Jake during stabilization window
48 | Confirm availability and monitoring in place for all separated Prod environments | Monitoring configured; availability baseline established; Saritha has visibility | 7 · Validation | You | No | Not Started | All | Do not leave Prod without measurement in place
49 | Collect user feedback from ~140 separated users; resolve reported issues | Feedback loop active; all P1/P2 issues resolved; log closed or transitioned | 7 · Validation | You + Saritha | No | Not Started | All | Establish feedback channel on Day 1 of Prod — don't wait for problems to find you
50 | Prod sign-off from Saritha | Written sign-off from Saritha confirming separated Prod migration complete and stable | 7 · Validation | Saritha | No | Not Started | All | Get this before contract end or extension conversation
PHASE 8 · CLOSEOUT
51 | Finalize consolidated dependency map and hand off as ongoing CMDB baseline | Clean, verified dependency document delivered to Jake and Saritha as the new single source of truth | 8 · Closeout | You | No | Not Started | All | This directly addresses the fragmented tracking problem identified in Discovery. It is one of the most valuable things you leave behind.
52 | Finalize and hand off all migration documentation | Complete runbooks, config docs, change logs delivered to Jake and Saritha | 8 · Closeout | You | No | Not Started | All | Documentation is part of the deliverable, not a nice-to-have
53 | Confirm decommission plan for old parent-company environments | Decommission timeline agreed; IT has plan; old servers not removed until sign-off | 8 · Closeout | Saritha + IT | Yes | Not Started | Infrastructure | Delegate — not your call, but flag it explicitly
54 | Contract extension or close-out discussion with Palmer Group | Extension terms confirmed in writing, OR close-out acknowledged and final invoice submitted | 8 · Closeout | You + Palmer Group | No | Not Started | All | Kristi / Sarah at The Palmer Group

## Legend & Color Key
LEGEND & COLOR KEY
ROW COLOR (Execution)
White — You (solo) | You own and execute this task alone, sequentially
Green — Parallel | Can run concurrently with other work
Blue — Delegate | Assign to Jake, SAS Admin, or IT; you validate output
Amber — Joint | Requires active input from both you and Corteva
STATUS
Not Started | Work has not begun
In Progress | Actively being worked on
Complete | All completion criteria met and verified
Blocked | Cannot proceed — dependency or issue unresolved
KEY NOTES
OS Target | Confirmed with Jake: latest supported Windows Server version (2022/2025 TBD). Get written confirmation before planning.
OS Upgrade Sequencing | Jake agreed: upgrade OS first, then execute separation. Phase 3 must complete before Phase 4.
Dependency Tracking | Jake indicated tracking is fragmented — no single source of truth. Phase 1 #9 builds the consolidated map that everything else depends on.
User Scope | ~140 users (35% of ~400 total) moving to new IT domain / new company in the separation.
2-Week Deliverable | Jake requested a next-steps presentation within 2 weeks of start. See Phase 2 #21.