## Timeline Analysis
CORTEVA MIGRATION — REALISTIC TIMELINE ANALYSIS
6-Month Contract Starting ~April 2026 ¦ Realistic Range: 6–10 Months ¦ Key threats identified below
BASELINE — OPTIMISTIC 6-MONTH SCHEDULE (everything goes right)
# | Phase | Start | End | Key Assumptions for This to Hold | Risk if Wrong
1 | Pre-Start & Access | Wk 1 | Wk 1 | Contract signed day 1; access to all environments granted within 48 hours | Access delays alone can cost 2–3 weeks
2 | Discovery & Dependency Audit | Wk 1 | Wk 3 | Jake and SAS Admin available; dependency tracking gaps manageable | Fragmented tracking (per Jake) could extend this to 6+ weeks
3 | Planning & OS Version Confirm | Wk 3 | Wk 5 | Target OS confirmed quickly; IT procurement already in motion | Licensing/procurement is an IT/finance decision — can take weeks
4 | OS Upgrade (all platforms, all tiers) | Wk 5 | Wk 10 | IT provisions servers fast; SAS/Spotfire/PBI compatible with target OS | Application compatibility testing alone can add 2–4 weeks
5 | Separation Build — Dev | Wk 9 | Wk 14 | New domain infrastructure ready; DB connection scope confirmed | New IT domain setup is an IT project in itself
6 | Sandbox + UAT | Wk 13 | Wk 18 | ~140 users available for UAT; sign-off obtained promptly | UAT scheduling with business users is notoriously slippery
7 | Prod Cutover + Validation | Wk 18 | Wk 22 | No critical issues found in Sandbox; go/no-go is clean | One major issue in UAT can push cutover 4–6 weeks
8 | Stabilization & Closeout | Wk 22 | Wk 26 | Post-cutover stable within 72 hours; documentation completed | Undiscovered dependencies surface post-cutover — common
THREATS TO THE 6-MONTH TIMELINE — Ranked by Likelihood
Risk | Threat | Likelihood | Weeks at Risk | Impact | Mitigation
T1 | Fragmented dependency tracking — no single source of truth (per Jake) | 🔴 HIGH | +2 to +6 wks | Discovery takes much longer than planned; migration built on incomplete map | Phase 1 #9 — audit ALL sources before touching anything
T2 | IT provisioning queue for new servers / new domain infrastructure | 🔴 HIGH | +2 to +4 wks | OS upgrade and separation build cannot start until IT provisions environments | Raise provisioning request on Day 1; track daily
T3 | OS / target version not confirmed; procurement / licensing delay | 🟠 MED-HIGH | +1 to +4 wks | Planning cannot lock down until version is confirmed; may affect hardware compat | Get written version confirmation in Week 1 kick-off
T4 | Application compatibility: SAS, Spotfire, or PBI Gateway not certified on target OS | 🟠 MED-HIGH | +2 to +6 wks | Could require vendor support calls, patches, or version upgrades of the apps themselves | Verify all three platform vendors' OS support matrix before upgrade begins
T5 | UAT scheduling delays — ~140 business users hard to coordinate | 🟠 MEDIUM | +1 to +4 wks | Sandbox sign-off gate blocked; Prod cutover window slips | Book UAT window early; get Saritha to own user scheduling
T6 | SAS admin knowledge gaps — Jake inherited role ~2.5 yrs ago, no formal handoff | 🟠 MEDIUM | +1 to +3 wks | Undocumented SAS configs surface during migration; rework required | Treat Discovery Phase as mandatory — do not skip or rush
T7 | Post-cutover undiscovered DB dependencies surface in Prod | 🟡 MED-LOW | +1 to +4 wks | ~140 users reporting issues; emergency stabilization period | Consolidated dependency map (#15 in checklist) is the prevention
T8 | Contract start delayed (hiring decision, onboarding, security clearance) | 🟡 MED-LOW | +1 to +3 wks | Entire timeline shifts right; 6-month window may not accommodate full scope | Discuss with Palmer Group; push for fast onboarding once offer accepted
T9 | Scope creep — additional platforms, users, or systems added mid-engagement | 🟡 MED-LOW | +2 to +6 wks | 6-month window blown; extension required | Define scope in writing at kick-off; any additions require contract amendment
REALISTIC OUTCOME SCENARIOS
Scenario | Duration | Likelihood | What Has to Be True | Recommendation
Best Case | 6 months | 🟡 20% | Access granted fast; dependency map clean; OS version confirmed Week 1; IT responsive; no app compat issues; UAT smooth | Plan for this; don't count on it
Most Likely | 7–8 months | 🔴 55% | 1–2 threats materialize (most likely: IT provisioning delay + dependency gaps); managed well but scope needs extension | Build extension language into contract from day one; flag at kick-off
Extended | 9–10 months | 🟠 20% | Multiple threats hit: app compat issue + UAT delays + dependency rework; no major disasters but steady friction | Raise at 3-month check-in if pace is behind; don't wait until Week 24
At Risk | 10+ months | 🟡 5% | Major undiscovered dependency or app incompatibility requires platform version upgrades or vendor involvement | Identify this risk in Week 3 Discovery report; surface immediately to Saritha
KEY RECOMMENDATION: Build a 2-month extension option into the contract from day one. The Most Likely scenario (7–8 months) is not a failure — it is a realistic outcome for a migration of this complexity with a new IT domain, ~140 users, fragmented dependency tracking, and an OS upgrade as a prerequisite. The 6-month window is achievable only if most of the HIGH-likelihood threats are resolved in the first 3 weeks.